## Implementation Plan
Implementation Plan
Project |  |  |  | Project Manager |  |  | Stakeholders | [5 empty] | Date Revised
[Name of project] |  |  |  | [Name of project manager] |  |  | [Names of primary stakeholders] | [5 empty] | [Month, day, year updated]
Strategy |  |  |  | Timeline | [5 empty] | Resources
Priority | Task | Assigned | Status | Planned Start | Actual Start | Planned Finish | Actual Finish | Ahead/Behind | Planned Hours | Department | Materials Required | Cost | Notes
High | Research | Erik B. | 100% | 2021-01-03 | 2021-01-05 | 2021-01-17 | 2021-01-15 | Ahead | 3 weeks | Research | JSTOR | 50
Medium | Analysis | Ryan J. | 75% |  |  |  |  | Behind | 1 week | Management |  | $
Low | Pitch strategies | Ryan J.. | 50% |  |  |  |  | On Schedule | 1 week | Management |  | $
| Select strategy | James C., Ryan J. | 0% | [5 empty] | 1 week | Management |  | $
Process |  |  |  | Timeline | [5 empty] | Resources
Priority | Task | Assigned | Status | Planned Start | Actual Start | Planned Finish | Actual Finish | Ahead/Behind | Planned Hours | Department | Materials Required | Cost | Notes
| Work breakdown structure | Joyce P. | 50% | [5 empty] | 2 weeks | Management |  | $
| Schedule | Sarah R. | 50% | [5 empty] | 2 weeks | Management |  | $
| Resources | John J. | 75% | [5 empty] | 1 week | Management |  | $
| Budget | Ryan J. | 25% | [5 empty] | 1 week | Management |  | $
Action |  |  |  | Timeline | [5 empty] | Resources
Priority | Task | Assigned | Status | Planned Start | Actual Start | Planned Finish | Actual Finish | Ahead/Behind | Planned Hours | Department | Materials Required | Cost | Notes
| Training | Ira S. | 50% | [5 empty] | 1 week | Third-party source |  | $
| Assignments | Ryan J. | 75% | [5 empty] | 2 weeks | Project team |  | $
| Monitoring and tracking | Ryan jJ. | 25% | [5 empty] | 2 weeks | Management |  | $
| Review | Ryan J. | 25% | [5 empty] | 2 weeks | Management |  | $

## How to Use This Template
Introduction
Before you can plan a project, you need to create an implementation plan. It outlines all three component needed in order to accomplish your goal: strategy, process and actions. This implementation plan template from ProjectManager has everything you need to start your project off right.
Definition of Terms
Priority: Notes whether the action is high, medium or low concern.
Task: A small action, one of the steps towards meeting a project goal.
Assigned: Has the task been assigned to a team member? Who?
Status: What is the percentage done?
Planned Start: When tast should initiate.
Actual Start: When the task in fact begins.
Planned Finish: When the task must be complete.
Actual Finish: When the task in fact is completed.
Ahead & Behind: Notes whether your on track or not.
Planned Hours: How long the task should take to get done.
Department: Which department is responsible for the task?
Materials Required: The material resources needed for the task.
Cost: Money allowed for task in budget.
Notes: Comments that don’t fall under other categories.